## Sheet1
When: 25/05/202025 09:00 AM |  | Who: Divik/Karan | Application: KDIV Limited
Note: please make sure you fill all information related to your project below and convert/include link to Wiki Or readme.md (GitHub)
ID | Scenario Title | Status | Scenario | Remarks
1 | Startup page | Pass | Given the user accesses the website, when the homepage loads, then the banner and menu should appear clearly. | Given the page loads, when viewing the layout, then it is mobile-optimized and loads quickly.
2 | Product notification | Pass | Given the user visits a product page, when stock is low, then a notification should appear. | Given the product page is open, when stock alert triggers, then it shows a clear notification.
3 | Add to cart functionality | Failed | Given a user selects a smartwatch, when they click "Add to cart", then the item should be added. | Given the user is on iOS Safari, when they click “Add to cart”, then an error occurs.
4 | Checkout process | Pass | Given items are in the cart, when the user proceeds to checkout, then they can complete the purchase. | Given the checkout is completed, when the order is placed, then an email is received.
5 | Mobile responsiveness | Pass | Given various smartwatch devices, when the site loads, then it should display correctly. | Given different screen sizes, when browsing the site, then content scales properly.
6 | Search functionality | Failed | Given the user is on the homepage, when they use the search bar, then search results should appear. | Given the user is on Android WebView, when they use search, then it does not respond.
7 | User login/signup | Pass | Given the user has no account, when they register or log in, then they can access personal features. | Given multiple login methods, when used, then they all work successfully.
8 | Wishlist saving | Pass | Given a logged-in user, when they click “Add to wishlist”, then the item is saved to their list. | Given an item is wishlisted, when accessed later, then it appears across devices.